## User Stories
Sensor Integration System — User Stories
Priority: ■ Must Have ■ Should Have ■ Could Have Status: ■ Complete ■ In Progress ■ Incomplete
ID | Role | I Want To... | So That... | Acceptance Criteria | Priority | Status
1 | User | Create an account | Access sensor information from a browser | User can successfully create an account with a unique + valid email, username, and password | Must Have | Complete
2 | User | Register a sensor | Collect data | User can successfully register a new device given a metric and unique ID | Must Have | Complete
3 | User | Name and add descriptions to sensors | Organize and identify devices | User can set a display name and device type for each sensor; both are shown on device cards (no separate long-text description field). | Must Have | Complete
4 | User | Change the password | Secure my account | User can set a new password from Profile (with confirmation); complexity rules enforced; re-login requires new password. (API: new password only — no current-password field.) | Must Have | Complete
5 | User | Delete a sensor | Remove unused devices | User can remove a sensor from the list of registered sensors through a button press | Must Have | Complete
6 | User | Log out of my account | No one can access my session | User can terminate their session by clicking the 'logout' button | Must Have | Complete
7 | User | Ensure my data is encrypted | Sensitive information is secure | Data is encrypted (bcrypt passwords, JWT tokens, HTTPS-ready) to prevent unauthorized access | Must Have | Complete
8 | User | Group sensors | Manage devices by area or function | User can create organizational units to organize sensors; consider click and drag | Should Have | Incomplete
9 | User | Add/remove members to/from a group | Share sensor information with others | User can create groups and invite members using another user's email address | Should Have | Incomplete
10 | User | Set permission levels for group members | Manage access and authorization | Group owner can modify each group member's privileges (view, modify, own) | Should Have | Incomplete
11 | User | View a log of collected sensor data | Track data over time | User can view logs for each sensor, displaying all data collected per device | Must Have | Complete
12 | User | Filter logged data by date/time | View data from specific events | User can apply date/time filters to log data to display matching records | Should Have | Complete
13 | User | Be notified of failed login attempts | Know about unauthorized login attempts | User receives an email alert on failed password attempts (optional toggle in Profile). Admin inbox receives forgot-password notifications. | Could Have | Complete
14 | User | Use MFA via SMS/email | Account is resilient to password compromise | Not implemented: SMS/email-delivered MFA. The app uses an in-browser 6-character verification step on login/signup only. | Should Have | Incomplete
15 | User | Session timeout after inactivity | Session is secure | User session terminates after configurable minutes of inactivity (timer displayed with countdown) | Could Have | Complete
16 | User | Edit data collection intervals | Manage battery life vs data volume | User can view and edit collection interval (minutes) per device in Edit Device; persisted via PATCH /api/devices/:id. | Should Have | Complete
17 | User | Export sensor data | Analyze data using separate tools | User can request a data file with logs for multiple sensors in CSV format | Should Have | Complete
18 | User | Create custom alert rules | Monitor complex scenarios | User can create rules based on sensor data that establish conditions to trigger alerts | Could Have | Incomplete
19 | User | View sensor data visually | Quickly interpret information | User can view line charts (temperature, humidity) for historical readings when View Data is open; Chart.js updates with filtered data. | Could Have | Complete
20 | User | Set thresholds for sensors | Receive alerts when values exceed limits | User can set custom values for each sensor's metrics to trigger alerts | Could Have | Complete
21 | User | Update account information | Alerts are sent to the right place | User can update email and phone from Profile; saved via PATCH /api/account. | Should Have | Complete
22 | User | Receive alerts | Aware of system functions | Email alerts sent when sensor readings breach configured thresholds (and on failed logins if enabled). SMS not implemented. | Should Have | Complete
23 | User | Update sensor firmware | Devices are secured and reliable | Prompted when updates available; firmware updated or error thrown | Should Have | Incomplete
24 | User | Monitor sensor connectivity | Quickly identify issues | Connectivity status displayed with sensors (online/offline), logging when switched on/off | Should Have | Complete
25 | User | Back up data regularly | Data is not lost | System has default automatic backups; can restore from backups | Should Have | Incomplete
26 | User | Schedule automated data exports | Integrate with external systems | User can configure an export schedule specifying which/where sensor data is sent with timestamps | Could Have | Incomplete
27 | User | Set data retention policies | Manage storage costs for relevant data only | User can configure how long each sensor stores data in the system | Should Have | Complete
28 | User | Edit sensor details | Repurpose devices | User can assign new names and descriptions to each sensor after initial registration | Should Have | Complete
32 | User | Scan QR/barcode to add device | Quickly register devices without typing IDs | User can use camera to scan QR code or barcode; Device ID is auto-filled in Add Device form | Could Have | Complete
▶ New Features Added — Authentication & Admin
29 | User | Lock account after failed attempts | Protect against brute-force attacks | Account is locked after 5 failed login attempts; user sees remaining attempts count before lockout | Must Have | Complete
30 | User | Recover account via forgot password | Regain access if password is forgotten | User submits email/phone; system sends temp password to admin via Gmail SMTP; user must change password on next login | Must Have | Complete
31 | User | Force password change after reset | Ensure account security after admin reset | User is shown a mandatory password change screen on next login after a temp password is issued; cannot skip | Must Have | Complete
39 | User | Self-deactivate my account | Temporarily disable account without losing data | User can deactivate account from Profile Danger Zone (must type DEACTIVATE); logged out immediately; data preserved 2 months then auto-deleted | Should Have | Complete
▶ Admin Panel Features
33 | Admin | View and manage all users | Oversee the system and handle user issues | Admin can view all users with role, status, device count; expand rows for full details (join date, last login, failed attempts) | Must Have | Complete
34 | Admin | Reset any user's password | Help users who are locked out | Admin generates a temp password shown in a copyable modal; user is flagged must_change_password on next login | Must Have | Complete
35 | Admin | Enable or disable user accounts | Control access to the system | Admin can toggle any user's active status; disabled users are blocked at every API call; action is logged | Must Have | Complete
36 | Admin | Unlock locked accounts | Restore access for users locked after failed logins | Admin can unlock any locked account with one click; resets failed attempt counter; action logged | Must Have | Complete
37 | Admin | View activity logs | Audit all administrative actions | Admin sees a table of the 100 most recent actions (disable, enable, reset PW, unlock, delete) with timestamp, actor, target, and IP | Must Have | Complete
38 | Admin | Permanently delete users | Remove accounts and all associated data | Admin can permanently delete a user; all devices and sensor data cascade-deleted; action requires confirmation and is logged | Must Have | Complete

## Summary
Project Summary — Sensor Integration System
Status Breakdown | Count | % of Total
Total Stories | 39
✅ Complete | 31 | 79%
🔄 In Progress | 0 | 0%
❌ Incomplete | 8 | 21%
Priority Breakdown | Total | Complete | % Done
Must Have | 17 | 17 | 100%
Should Have | 15 | 9 | 60%
Could Have | 7 | 5 | 71%
✨ 31 of 39 stories Complete · Sprint 3 of 3 done · 8 PBI remaining · Avg velocity: 10.3 PBI/sprint

## Sprint Review
Sensor Integration System — Sprint Review
Velocity & Estimate to Complete
Total Product Backlog Items (PBI): |  |  | 39 |  | Sprint | Remaining | Ideal
PBI Completed (Sprint 1 + Sprint 2 + Sprint 3): |  |  | 31 |  | Sprint 0 (Baseline) | 38 | 38
Remaining PBI: |  |  | 8 |  | Sprint 1 | 28 | 19
Average PBI / Sprint (velocity): |  |  | 10.3 |  | Sprint 2 | 19 | 0
Sprints Completed: |  |  | 3 |  | Sprint 3 | 10 | 0
Estimated Sprints to Complete Remaining: |  |  | 1
Sprint Duration: |  |  | 2 weeks
Sprint Summary
Sprint | Dates | PBI This Sprint | Cumulative Done | Remaining PBI | Items Covered
Sprint 0 (Baseline) | — | — | 0 | 38 | Project kickoff — all PBI identified
Sprint 1 | Feb 11 – Feb 25 | 10 | 10 | 28 | Account creation, login, verification code, password rules, JWT auth, session timeout, device management, encryption
Sprint 2 | Feb 25 – Mar 11 | 9 | 19 | 19 | Account lockout, forgot password, force PW change, self-deactivate, full admin panel, activity logs, user management
Sprint 3 | Mar 11 – Mar 30 | 10 | 31 | 8 | Sensor log, date filter, export CSV/JSON, QR scan, thresholds, threshold & failed-login email alerts, connectivity status, data retention, edit sensor, collection interval, charts, profile email/phone
Cumulative Product Backlog Item Status
PBI / User Story | Acceptance Criteria (Summary) |  |  |  |  | Sprint # | Start Date | End Date | Status
▶ Sprint 1 (Feb 11 – Feb 25)
#1 Create an account | Email/phone + username, password complexity enforced, duplicate check |  |  |  |  | Sprint 1 | Feb 11 | Feb 25 | Done
#2 Register a sensor | Register new device with unique ID and metric type |  |  |  |  | Sprint 1 | Feb 11 | Feb 25 | Done
#3 Name and add descriptions to sensors | Add names and descriptions to each registered sensor |  |  |  |  | Sprint 1 | Feb 11 | Feb 25 | Done
#4 Change the password | Edit password with current + new password, complexity requirements enforced |  |  |  |  | Sprint 1 | Feb 11 | Feb 25 | Done
#5 Delete a sensor | Remove sensor from list via button; all associated data cascade-deleted |  |  |  |  | Sprint 1 | Feb 11 | Feb 25 | Done
#6 Log out of my account | Session terminated on logout; JWT token cleared |  |  |  |  | Sprint 1 | Feb 11 | Feb 25 | Done
#7 Ensure my data is encrypted | Passwords hashed with bcrypt; sessions secured via JWT tokens |  |  |  |  | Sprint 1 | Feb 11 | Feb 25 | Done
#14 Use MFA via SMS/email | #14 Verification step on login/signup (not SMS/email MFA — full MFA remains Incomplete in User Stories sheet) |  |  |  |  | Sprint 1 | Feb 11 | Feb 25 | Done
#15 Session timeout after inactivity | Configurable timeout in minutes; countdown shown; auto-logout on expiry |  |  |  |  | Sprint 1 | Feb 11 | Feb 25 | Done
#29 Lock account after failed attempts | Account locked after 5 failed attempts; remaining count shown; admin can unlock |  |  |  |  | Sprint 1 | Feb 11 | Feb 25 | Done
▶ Sprint 2 (Feb 25 – Mar 11)
#30 Recover account via forgot password | Temp password generated and emailed to admin via Gmail SMTP; user notified |  |  |  |  | Sprint 2 | Feb 25 | Mar 11 | Done
#31 Force password change after reset | Mandatory change screen shown after temp PW login; cannot be dismissed |  |  |  |  | Sprint 2 | Feb 25 | Mar 11 | Done
#32 Self-deactivate my account | Must type DEACTIVATE; logged out immediately; data kept 2 months then auto-deleted |  |  |  |  | Sprint 2 | Feb 25 | Mar 11 | Done
#33 View and manage all users | Admin sees all users with role, status, device count; click row for full details |  |  |  |  | Sprint 2 | Feb 25 | Mar 11 | Done
#34 Reset any user's password | Generates temp password in copyable modal; user flagged must_change_password |  |  |  |  | Sprint 2 | Feb 25 | Mar 11 | Done
#35 Enable or disable user accounts | Toggle active status; disabled users blocked at all API calls; action logged |  |  |  |  | Sprint 2 | Feb 25 | Mar 11 | Done
#36 Unlock locked accounts | One-click unlock resets failed attempt counter; action logged |  |  |  |  | Sprint 2 | Feb 25 | Mar 11 | Done
#37 View activity logs | Last 100 admin actions with timestamp, actor, target, IP address |  |  |  |  | Sprint 2 | Feb 25 | Mar 11 | Done
#38 Permanently delete users | Cascade-deletes all devices and sensor data; requires confirmation; logged |  |  |  |  | Sprint 2 | Feb 25 | Mar 11 | Done
▶ Sprint 3 (Mar 11 – Mar 30)
#11 View a log of collected sensor data | Sensor log shows all readings per device; paginated, sortable |  |  |  |  | Sprint 3 | Mar 11 | Mar 30 | Done
#12 Filter logged data by date/time | From/to date-range filters applied to sensor log; results update |  |  |  |  | Sprint 3 | Mar 11 | Mar 30 | Done
#13 Be notified of failed login attempts | Email alert on every failed login; toggle via account settings |  |  |  |  | Sprint 3 | Mar 11 | Mar 30 | Done
#17 Export sensor data | CSV and JSON export with date-range and limit filters; auto-named file |  |  |  |  | Sprint 3 | Mar 11 | Mar 30 | Done
#20 Set thresholds for sensors | Min/max per metric (temp, humidity, pressure) configurable per device |  |  |  |  | Sprint 3 | Mar 11 | Mar 30 | Done
#22 Receive alerts (threshold breach) | Email sent when reading breaches min/max; includes values and device info |  |  |  |  | Sprint 3 | Mar 11 | Mar 30 | Done
#24 Monitor sensor connectivity | Online/offline badge per device; offline after 5 min without a reading |  |  |  |  | Sprint 3 | Mar 11 | Mar 30 | Done
#27 Set data retention policies | retention_days per user (1–3650 days); nightly purge job deletes old data |  |  |  |  | Sprint 3 | Mar 11 | Mar 30 | Done
#28 Edit sensor details | Name, type, collection interval and thresholds editable after registration |  |  |  |  | Sprint 3 | Mar 11 | Mar 30 | Done
#32 Scan QR/barcode to add device | Camera scanner auto-fills Device ID; supports QR codes and barcodes |  |  |  |  | Sprint 3 | Mar 11 | Mar 30 | Done